## Tabelle1
Identified | Description | prob of occurence (in %) | damage/impact (1-10) | mitigation strategy | person in charge | risk factor (0-10)
showstopper at critical time | changes in code lead to an fatal error, before presentation | 0.6 | 7 | splitting branches in master, develop (Git Workflow); regular testing in the end; feature freeze | Maurice | 4.2
loss of data | due to device failure; | 0.3 | 10 | code management using GitHub; track code sharing | Alex | 3
underestimated workload | to much workload of this course regarding the workload of other courses | 0.5 | 5 | flexible workload management | Alex | 2.5
server shutdown | shutdown due to failure/updates | 0.3 | 7 | update freeze before endpresentation; backups; docker | Mirko | 2.1
illness | fatal | 0.3 | 2 | code sharing; communication via WhatsApp; regular commits to feature branches |  | 0.6
loss of team members | loss of team members due to exmatriculation | 0.07 | 8 | share knowledge via GitHub; document detailed | Alex | 0.56
0
0
0