## Tabelle1
UC | Documentation | Coding | Testing | Total | Warm-Up Time | FP
relay messages | 2h | 12h | 5h | 20h | 5h
manage session | 1h | 10h | 1h | 12h | 5h
create identity | 1h | 6h | 1h | 8h | 3h
send message | 2h | 10h | 3h | 15h | 8h
receive message | 2h | 10h | 2h | 14h | 6h
share files | 1h
chat geo-localized | 1h
encrypted chat | 1h
manage lobby | 1h
visualize lobby | 1h

## Tabelle2
use case | esitmation (h) | logged (h) | transaction | DET | RET | FTR | Complexity | function points | UC | Funktion Ponts | Use Case
[9 empty] | create identity | 16.8 | 8
relay messages | 20h |  | external input | 0 |  |  | low |  | manage session | 34.6 | 12
|  |  | external output | 2 |  |  | low |  | receive message | 46.2 | 14
|  |  | external inquieries | 0 |  |  | low |  | send message | 48.3 | 15
|  |  | internal logical files |  | 7 |  | avg |  | relay messages | 81.9 | 20
|  |  | external interface files | 0 |  |  | low | 81.9
manage session | 12h |  | external input | 0 |  |  | low |  | New Use Cases
|  |  | external output | 1 |  |  | low |  | share files | 19.9 | 9.1184
|  |  | external inquieries | 1 |  |  | low |  | chat geo-localized | 27.3 | 10.4689
|  |  | internal logical files |  |  | 3 | low |  | encrypted chat | 34.6 | 11.8012
|  |  | external interface files |  |  | 1 | low | 34.6 | manage lobby | 46.6 | 13.9912
[9 empty] | visualize lobby | 34.9 | 11.8559
create identity | 8h |  | external input | 0 |  |  | low
|  |  | external output |  | 1 |  | low
|  |  | external inquieries | 0 |  |  | low
|  |  | internal logical files | 1 |  |  | low
|  |  | external interface files | 1 |  |  | low | 16.8
send message | 15h |  | external input | 1 | 1 |  | low
|  |  | external output |  | 1 |  | low
|  |  | external inquieries | 0 |  |  | low
|  |  | internal logical files |  |  | 3 | low
|  |  | external interface files |  |  | 3 | low | 48.3
receive message | 14h |  | external input | 0 |  |  | low
|  |  | external output | 1 | 1 |  | low
|  |  | external inquieries | 0 |  |  | low
|  |  | internal logical files |  |  | 3 | low
|  |  | external interface files |  |  | 3 | low | 46.2
share files |  |  | external input | 1 |  |  | low
|  |  | external output | 1 |  |  | low
|  |  | external inquieries | 0 |  |  | low
|  |  | internal logical files |  |  | 1 | low
|  |  | external interface files |  |  | 1 | low | 19.9
chat geo-localized |  |  | external input | 1 |  |  | low
|  |  | external output | 1 |  |  | low
|  |  | external inquieries | 0 |  |  | low
|  |  | internal logical files | 1 |  | 1 | low
|  |  | external interface files | 1 |  |  | low | 27.3
encrypted chat |  |  | external input | 0 |  |  | low
|  |  | external output | 0 |  |  | low
|  |  | external inquieries | 0 |  |  | low
|  |  | internal logical files | 1 |  | 3 | low
|  |  | external interface files | 1 |  | 1 | low | 34.6
manage lobby |  |  | external input | 1 |  |  | low
|  |  | external output | 0 |  |  | low
|  |  | external inquieries | 0 |  |  | low
|  |  | internal logical files |  |  | 3 | low
|  |  | external interface files |  |  | 4 | low | 46.6
visualize lobby |  |  | external input | 0 |  |  | low
|  |  | external output | 1 |  |  | low
|  |  | external inquieries | 1 |  |  | low
|  |  | internal logical files |  |  | 3 | low
|  |  | external interface files |  |  | 1 | low | 34.9